JEWELL PROJECTS

Design Phase Strategy – Draft

| ENGAGEMENT | Adam Hall Buy My Car – Operating System engagement |
| --- | --- |
| STATUS | Draft v01 – pre-validation, to be updated after the session with Adam |
| AUDIENCE | Internal – Jewell Projects and Clent Jewell |
| DATE | 15 July 2026 |
| SUPERSEDES | n/a |
| PREPARED BY | Jewell Projects |

Purpose

This document sets the Design phase strategy for Adam Hall Buy My Car. It is a pre-validation draft – nothing here is confirmed with Adam yet, but the shape we intend to test with him.

Design has one job: turn what lives in Adam's head into things other people can run. The asset we are building is the Adam Hall Operating System – the documented version of how the business actually works – plus the brand and sales architecture around it. Every artefact should make Adam's judgement usable by someone who is not Adam.

What Design Inherits from Discover

Design does not invent. It consumes the Re-Discover mapping output – sessions capturing Adam's decision rules, trust technique and operating patterns in LIGHT and FULL mode – and turns that into SOPs, scripts, valuation rules, hiring briefs, brand direction and training content.

The structure below is a target, not a finished set. Some cells stay thin until a matching session happens. A visible gap beats an invented answer.

Customer Profile (Hypothesis)

PAIN. Mostly 60–75+, selling a car tied to a life change – downsizing, losing a licence, an estate after a death, a health event that ends driving. The car can be a late parent's, or the last big decision before a smaller life. Fear of being ripped off runs high, and so does fear of the process – paperwork, technology, strangers.

GAIN. Relief, not a negotiation win. A fair number delivered without pressure, plain-language explanation at each step, and certainty the money and paperwork will be handled properly.

PROOF. Word of mouth and Adam's radio heritage are believed to be the dominant proof mechanism today – hypothesis, to be confirmed. Home visits appear to be a key proof moment for anxious sellers. Volume and repeat pattern (~25 cars/month, ~90% retail) suggest trust is earned and retained, but the proof points customers actually cite have not yet been mapped.

Brand Strategy Direction (Hypothesis)

Positioning direction: trust before transaction. Adam Hall Buy My Car is not competing on the cheapest offer – it is competing on being the offer the customer does not need to second-guess. The Adam Hall Standard is the operating proof: empathy first then the solution, ownership not excuses, staying in the room until the customer is genuinely settled. That should carry into every channel, not just tone of voice.

Open question – flagged, not decided: does the brand carry Adam's personal name? His name is the current trust asset, built through decades of radio presence and word of mouth. But a name-carrying brand is harder to sell and scale past one person, which cuts against a brand that does not depend on him. This is the biggest brand decision in the engagement, and it needs Adam's answer.

Offer Architecture (Hypothesis)

Core offer, as currently understood: a fast, fair, no-pressure valuation and purchase, handled with the same care whether the sale nets $500 or $50,000 gross. The ~90/10 retail/wholesale split suggests most cars move through a channel that protects margin – the ~$4,200 average retail gross per car is the number to keep protecting as volume scales toward $7M. Speed and certainty for the customer, margin discipline for the business. Needs testing against real valuation examples before it is locked.

The Adam Hall Operating System

The centrepiece of Design: the inventory of assets that turn Adam's judgement into something teachable, repeatable and, where appropriate, automatable. JewellAI keeps this current as sessions bank fresh judgement; nothing here replaces a trust moment, it documents it so it can be trained.

| Asset | What it captures | Built from | High-control? |
| --- | --- | --- | --- |
| Lead qualification script | Sorting a real seller from a time-waster early | Mapping sessions | No |
| Home-visit trust playbook | Building trust in person; reading a grieving customer | Mapping sessions, trust cases | No |
| Valuation decision rules | The logic behind a number – what moves it up or down | Mapping sessions | No |
| Yes/no decision tree | The rule that flips Adam's instinct from yes to no | Mapping sessions | No |
| Wholesale/retail routing rule | How a car is sorted into the retail or wholesale channel | Mapping sessions | No |
| Payment and settlement checklist | Every step from agreed price to funds and paperwork settled | To be confirmed with Adam | Yes |
| PPSR / ID verification procedure | Checking finance owing and identity before a deal proceeds | To be confirmed with Adam | Yes |
| Rego transfer procedure | Steps that legally move ownership from seller to buyer | To be confirmed with Adam | Yes |
| Referral ask script | How and when Adam asks for a referral, in his own words | Mapping sessions | No |
| Values-first hiring brief | The Standard as a hiring filter – values first, skills second | Mapping sessions, George case | No |
| Onboarding and training programme | Bringing a hire to the Standard; trust moments train, not replace, judgement | All rows above | No |
| Daily standards rhythm | The self-criticism ritual made teachable | Mapping sessions | No |

Three assets touch money, identity or ownership transfer and are marked high-control. Nothing in those rows is treated as documented until Adam confirms it directly.

Sales on a Page (Draft)

| Stage | What happens | Owner | Trust moment |
| --- | --- | --- | --- |
| Lead in | Customer enquires, often via referral or radio-built awareness | Adam | First voice on the phone sets the tone |
| Qualification | Adam sorts genuine sellers, gathers car and situation detail | Adam | Listening for the real reason behind the sale |
| Valuation | Car assessed, often at the customer's home | Adam | The home visit – reassurance alongside the number |
| Yes/no decision | Adam decides the deal, the number, retail or wholesale | Adam | Is the number fair – trust is tested |
| Payment and settlement | Funds move, PPSR and ID checks done, ownership transferred | Adam (high-control) | Certainty the paperwork is handled properly |
| Close and referral ask | Deal settled, customer asked for a referral | Adam | The impression that decides if they tell a friend |

Draft shape only. Stage ownership and any handoffs beyond Adam need testing against real cases.

Team and Hiring Design

The Standard has to be hired for, not trained in after the fact – George is the proof of what happens when skills are hired first and values are assumed. The hiring brief sets the filter: empathy first then the solution, daily self-criticism, ownership not excuses, staying in the room. Skills are teachable against the SOPs once those values are in place; the values are not.

A first hire's first 90 days should prove the person can hold the Standard under real pressure, not just follow a script. What that proof looks like is an open question, below.

CORE Questions for Adam

| Code | Question | Why it matters | What the answer locks |
| --- | --- | --- | --- |
| CQ11 | Does the brand carry your personal name, or a name that can be sold independently of you? | Your name is the trust asset today, harder to transfer at scale | Brand direction, naming strategy |
| CQ12 | What are the non-negotiables a hire must never breach, even once? | The Standard needs hard edges, not just a spirit | Hiring brief, grounds for dismissal |
| CQ13 | Which parts of the customer conversation do you believe only you can do, and why? | Separates what can be scripted from what depends on you | Scope of the trust playbook |
| CQ14 | What must a first hire's first 90 days prove before you'd trust them alone? | Defines the onboarding bar, not just activity | Onboarding pass criteria |
| CQ15 | How would you know a valuation done by someone else was right? | Surfaces the check behind the decision | Valuation rules, yes/no tree |
| CQ16 | What does the referral ask sound like in your own words? | The script has to sound like you | The referral ask script |

Gate 2 Criteria

Design closes when:

- Customer Profile, Brand Strategy Direction and Offer Architecture are tested with Adam, moved from hypothesis to validated, or flagged as open.

- The naming question (CQ11) has an answer, even if it is "not yet."

- The Operating System inventory has real content behind every non-high-control row.

- All three high-control assets are confirmed directly with Adam, with no invented compliance detail.

- The hiring brief and onboarding programme are specific enough to run a real hire through.

- Adam has signed off the Sales on a Page draft as accurate.

Pending Validation

- Brand naming direction (personal name versus new brand name) – open, CQ11.

- Customer Profile PROOF – radio heritage and word of mouth, not yet confirmed.

- Offer Architecture margin logic at scale – needs real valuation examples.

- Sales on a Page stage ownership beyond Adam – draft only.

- All three high-control Operating System assets – to be confirmed with Adam.

- First-hire 90-day proof criteria – open, CQ14.

Feeds Into

Once Gate 2 closes, the validated Operating System, brand direction and Sales on a Page feed into Deploy – where the SOPs, scripts and hiring brief are activated, Maxxim runs the marketing system, and the business begins operating on the documented version of itself rather than on Adam alone.